These 10 activities collectively simulate the responsibilities of a Project Cost Manager at ABC Infrastructure Ltd. Based on the analysis of the 120-record dataset, the consolidated managerial findings are as follows.

| Activity | Key Findings |
| --- | --- |
| Budget Overrun Analysis | 91 materials (75.83%) are Over Budget. Paint has the highest cumulative cost overrun. |
| Vendor Performance | BuildSupply is the highest-performing vendor based on the performance score analysis. |
| Delivery Delay Analysis | Delivery delays range from 1–8 days. The average delay is approximately 4 days. |
| Site-wise Cost Analysis | Mumbai has the highest material expenditure (₹2.87 Crores approximately). |
| Procurement Monitoring | In Transit materials (41) require immediate monitoring. |
| Project Phase Analysis | Foundation phase has the highest material expenditure. |
| Quality Assessment | Quality ratings do not strongly influence budget performance. |
| Cost Variance Analysis | Delay and cost variance show a very weak positive relationship (Correlation ≈ 0.089). |
| Dashboard Development | Six KPIs and five management filters are recommended. |
| Managerial Reporting | Procurement optimization and vendor management require immediate attention. |

### Activity 1: Budget Overrun Investigation

#### Prompt:

- Which materials have exceeded their planned costs?

- Identify the Top-10 materials with the highest cost variance.

- What percentage of materials are over budget?

- Suggest three cost-control measures to reduce future overruns.

#### Findings

- Materials exceeding their planned costs: 91 records (75.83%)

- Largest cost overruns were observed in:

  - Paint

  - Tiles

  - Steel

  - PVC Pipes

  - Bricks

#### Top-10 Materials by Cost Variance

| Rank | Material |
| --- | --- |
| 1 | Paint |
| 2 | Tiles |
| 3 | Steel |
| 4 | PVC Pipes |
| 5 | Bricks |
| 6 | Cement |
| 7 | Electrical Cables |
| 8 | Sand |
| 9 | Aggregate |
| 10 | Glass |

#### Cost-Control Measures

- Implement weekly procurement reviews.

- Adopt vendor-wise rate contracts for bulk purchases.

- Maintain material consumption dashboards for real-time cost monitoring.

### Activity 2: Vendor Performance Evaluation

#### Prompt:

- Which vendor has the highest overall performance rating?

- Compare vendors based on delivery delays, cost performance, and quality ratings.

- Identify the vendor responsible for the maximum delayed deliveries.

- Recommend whether the company should continue or discontinue any vendor.

#### Findings

| Vendor | Performance |
| --- | --- |
| BuildSupply | Highest |
| Prime Materials | Good |
| Metro Traders | Moderate |
| Sky Infra | Moderate |
| Ultra Vendors | Lowest |

#### Recommendation

| Vendor | Decision |
| --- | --- |
| BuildSupply | Continue |
| Prime Materials | Continue |
| Metro Traders | Continue with monitoring |
| Sky Infra | Performance improvement required |
| Ultra Vendors | Performance review recommended |

### Activity 3: Delivery Delay Risk Analysis

#### Prompt:

- Which materials experienced delivery delays?

- Which site has the maximum delayed deliveries?

- What is the average delivery delay across the project?

- Identify the materials causing critical delays (>5 days).

#### Findings

- Average delivery delay ≈ 4 Days.

- Delay range: 1–8 Days.

#### Critical Delays

| Category | Delay |
| --- | --- |
| Minor | 1–2 Days |
| Moderate | 3–5 Days |
| Critical | >5 Days |

#### Recommendations

- Maintain a two-week procurement look-ahead schedule.

- Develop alternate vendor arrangements.

- Monitor materials in transit daily.

### Activity 4: Site-wise Cost Analysis

#### Prompt:

- Which site has the highest total actual material cost?

- Compare planned and actual costs across all sites.

- Which site has the highest percentage of over-budget materials?

- Suggest measures to improve site-wise cost management

| Site | Actual Cost |
| --- | --- |
| Mumbai | Highest |
| Nagpur | Second Highest |
| Nashik | Moderate |
| Pune | Lowest |

#### Recommendations

- Site-wise budget allocation.

- Monthly cost audits.

- Material reconciliation statements.

### Activity 5: Procurement Status Monitoring

#### Prompt:

- How many materials are Delivered, In Transit, or PO Issued?

- Which materials are still awaiting delivery?

- Identify procurement bottlenecks affecting project progress.

- Suggest an effective procurement monitoring strategy.

| Status | Count |
| --- | --- |
| In Transit | 41 |
| Delivered | 40 |
| PO Issued | 39 |

#### Procurement Issues

- Delayed deliveries.

- Materials remaining in transit.

- Vendor dependency risks.

#### Recommendation

Implement:

- Daily Procurement Reports

- Material Tracking Dashboards

- Vendor Performance Monitoring

### Activity 6: Project Phase Cost Management

#### Prompt:

- Which project phase has the highest total material cost?

- Compare Foundation, RCC, Masonry, and Finishing costs.

- Which phase has the maximum budget overrun?

- Recommend strategies to optimize costs during critical phases.

| Project Phase | Ranking |
| --- | --- |
| Foundation | Highest |
| RCC | Second |
| Finishing | Third |
| Masonry | Fourth |

#### Recommendations

- Strengthen Foundation phase cost monitoring.

- Adopt phase-wise procurement planning.

- Review material wastage weekly.

### Activity 7: Material Quality Assessment

#### Prompt:

- Categorize materials based on Excellent, Good, and Average quality ratings.

- Does quality influence vendor performance?

- Is there any relationship between material quality and budget status?

- Recommend a material quality control framework.

| Rating | Records |
| --- | --- |
| Excellent | 42 |
| Good | 41 |
| Average | 37 |

#### Observation

- No strong relationship exists between:

  - Quality Rating

  - Vendor Performance

  - Budget Status

#### Quality Framework

Implement:

- Incoming Material Inspection

- Vendor Audits

- Material Testing Procedures

- Quality Checklists

- NCR Reporting Systems

### Activity 8: Cost Variance & Delay Analysis

#### Prompt:

- Calculate the relationship between Delivery Delay Days and Cost Variance.

- Does a longer delay generally increase material costs?

- Which materials experienced both delays and cost overruns?

- Suggest methods to minimize the financial impact of delivery delays.

| Parameter | Value |
| --- | --- |
| Correlation | 0.089 |
| Relationship | Very Weak Positive |

#### Conclusion

Longer delivery delays do not necessarily increase material costs.

Other factors affecting costs include:

- Price escalation

- Procurement practices

- Vendor pricing

- Quantity variations

- Site requirements

#### Recommendations

- Maintain safety stock.

- Adopt buffer procurement planning.

- Monitor delayed deliveries through dashboards.

### Activity 9: Material Consumption Dashboard

#### Prompt:

- Create KPIs for:

  - Total Planned Cost

  - Total Actual Cost

  - Total Cost Variance

  - Delivery Delays

  - Vendor Performance

  - Procurement Status

- Which visualizations are most suitable for management reporting?

- Design five dashboard filters useful for project managers.

#### Recommended KPIs

- Total Planned Cost

- Total Actual Cost

- Total Cost Variance

- Delivery Delays

- Vendor Performance

- Procurement Status

- Budget Utilization %

- Material Consumption Trends

#### Recommended Visualizations

- Bar Charts

- Pie Charts

- Treemaps

- KPI Cards

- Line Charts

- Vendor Scorecards

- Heat Maps

#### Dashboard Filters

- Site

- Vendor

- Material

- Project Phase

- Procurement Status

### Activity 10: Managerial Decision-Making Report

#### Prompt:

Prepare a management report answering the following questions:

- Which material recorded the highest actual cost?

- Which vendor performed the best and why?

- Which site incurred the highest expenditure?

- What percentage of materials exceeded the budget?

- Which project phase requires immediate cost control?

- What procurement issues were identified?

- How can delivery delays be reduced?

- Which KPIs should management monitor regularly?

- What are your Top-5 recommendations for improving project performance?

- Should ABC Infrastructure Ltd. revise its procurement strategy for future projects? Justify your answer.

#### Executive Summary

| Question | Answer |
| --- | --- |
| Highest Actual Cost Material | Tiles |
| Best Performing Vendor | BuildSupply |
| Highest Cost Site | Mumbai |
| Over Budget Materials | 75.83% |
| Highest Cost Phase | Foundation |
| Procurement Concern | High number of materials In Transit |
| Delay Reduction Strategy | Advance procurement planning |
| Important KPIs | Cost, Delay, Vendor Performance, Procurement Status |
| Procurement Revision Required | Yes |

#### Top-5 Recommendations

- Implement weekly cost variance reporting.

- Develop vendor scorecards for procurement decisions.

- Strengthen procurement planning for Foundation and RCC activities.

- Adopt site-wise material tracking dashboards.

- Introduce monthly budget performance reviews.

#### Final Managerial Conclusion

ABC Infrastructure Ltd. should revise its procurement strategy for future projects. With 75.83% of materials exceeding their planned costs and significant expenditures concentrated in the Foundation phase, the organization should prioritize vendor performance management, proactive procurement planning, and real-time cost monitoring. Establishing site-wise dashboards and implementing periodic cost variance analyses will significantly improve budget control, reduce procurement risks, and enhance overall project performance.